## Sheet1
User Story | User Story Description | Task Type | Task Description | Duration | Status
User Story 1 | As an HR employee, I want to view all employee details so that I can manage their vacation requests. | Backend | Create API endpoint to fetch all employee details. | 2-3 hours | 1
|  | Backend | Implement authorization to ensure only HR employees can access this data. | 3-4 hours
|  | Backend | Fetch data from the database and return employee details. | 2-3 hours
|  | Frontend | Create Employee List Component to display employee details(Full Name, Role , Vacation Balance)
|  | Frontend | Implement Service to fetch data from the backend API.
|  | Frontend | Design UI for displaying employee details.
User Story 2 | As a normal employee, I want to view my own details so that I can track my vacation balance and request off days. | Backend | Create API endpoint to fetch logged-in employee’s details. | 2-3 hours
|  | Backend | Ensure employees can only access their own data via role-based authorization. | 3-4 hours
|  | Frontend | Create Employee Profile Component for displaying employee details.
|  | Frontend | Design UI to show vacation balance and other personal details.
User Story 3 | As an employee, I want to request an off day so that HR can approve or reject it. | Backend | Create API endpoint to submit leave request with start/end dates and reason. | 2-3 hours
|  | Backend | Validate that the employee has enough vacation balance before submitting the request. | 3-4 hours
|  | Frontend | Design UI for displaying employee leave request form.
User Story 4 | As an HR employee, I want to approve or reject off day requests so that employees can receive confirmation about their leave status. | Backend | Create API endpoint for HR to approve/reject leave requests. | 2-3 hours
|  | Backend | UserUpdate leave request status to approved/rejected in the database. | 2-3 hours
|  | Backend | Send notification to employee with approval/rejection outcome. | 2-3 hours
User Story 5 | As an employee, I want to see the status of my off day request so that I know whether it has been approved, rejected, or is still pending. | Backend | Create API endpoint to fetch leave request status for the employee. | 2-3 hours
|  | Frontend | Display leave request status (pending, approved, rejected) in the employee profile.
User Story 6 | As an HR employee, I want to manage vacation days so that the system reflects the correct remaining balance for employees. | Backend | Create API endpoint to update vacation balance after approved leave days. | 2-3 hours
|  | Backend | Update vacation balance in the database after leave approval. | 2-3 hours
|  | Frontend | Design UI for HR to manage vacation balances and approve leave requests.